## Title Epic User Story Priority
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate (Days) | Actual Effort (Days)
1 | UI Enhancements | User Interface | As a user, I want a visually appealing and intuitive interface, so I can easily navigate and use the app. | Must Have | To Do | - Modern and clean design. <br> - Clear navigation. <br> - Responsive design for different screen sizes. | - Improve color scheme and typography. <br> - Optimize button placement and size. <br> - Ensure responsiveness across devices. | - Visually appealing. <br> - User-friendly. <br> - Consistent branding. | 5 | TBD
2 | Recipe Generation | LLM Language Generation | As a user, I want the app to generate creative and diverse recipe suggestions based on my dietary needs and preferences, so I can discover new and exciting meals. | Must Have | To Do | - Generate recipes based on user input (ingredients, dietary restrictions, cuisine). <br> - Ensure recipe diversity and avoid repetition. <br> - Provide clear and easy-to-follow instructions. | - Develop LLM model for recipe generation. <br> - Integrate model with user input. <br> - Implement recipe formatting and presentation. | - Accuracy of generated recipes. <br> - Creativity and diversity of suggestions. <br> - Clarity and conciseness of instructions. | 10 | TBD
3 | Model Accuracy | Model Evaluation | As a developer, I want to continuously evaluate and improve the accuracy of the recipe generation model, so I can ensure users receive reliable and relevant suggestions. | Must Have | To Do | - Define metrics for evaluating model performance (accuracy, relevance, diversity). <br> - Implement automated testing and evaluation. <br> - Collect user feedback on generated recipes. | - Develop evaluation metrics and tools. <br> - Implement A/B testing for model comparison. <br> - Integrate user feedback mechanisms. | - Reliability of evaluation metrics. <br> - Efficiency of testing process. | 7 | TBD
4 | Critical Bug Fixes | Bug fixes | As a user, I want the app to be free of critical bugs that affect core functionality, so I can have a smooth and seamless experience. | Must Have | To Do | - Identify and prioritize critical bugs. <br> - Fix bugs related to recipe generation, user input, and app stability. <br> - Thoroughly test bug fixes before release. | - Implement bug tracking and reporting system. <br> - Develop and apply bug fixing procedures. | - App stability and reliability. | 3 | TBD
5 | User Feedback Integration | Feedback | As a developer, I want to collect and analyze user feedback on the app, so I can identify areas for improvement and enhance user satisfaction. | Could Have | To Do | - Implement in-app feedback mechanisms (surveys, feedback forms). <br> - Analyze user feedback data. <br> - Prioritize and address user concerns. | - Develop user feedback collection tools. <br> - Implement data analysis and visualization. | - User-friendliness of feedback mechanisms. <br> - Efficiency of feedback analysis. | 4 | TBD
6 | Adjustable Servings | Servings | As a user, I want to be able to adjust the number of servings for each recipe, so I can easily cook for different group sizes or meal prep for the week. | Should Have | To Do | - Allow users to input desired servings. <br> - Automatically adjust ingredient quantities based on servings. | - Develop serving adjustment feature. <br> - Integrate with recipe generation and display. | - Accuracy of ingredient adjustments. | 2 | TBD
7 | Dietary Filters | Diet | As a user, I want to be able to filter recipes by various dietary restrictions (vegetarian, vegan, gluten-free, etc.), so I can easily find recipes that meet my needs. | Must Have | To Do | - Implement dietary filters. <br> - Ensure accurate tagging of recipes with dietary information. | - Develop dietary filter functionality. <br> - Integrate with recipe database and search. | - Accuracy of dietary information. <br> - User-friendliness of filters. | 3 | TBD
8 | Responsive | Lite/Dark mode | As a user, I want to be able to switch between lite and dark modes in the app, so I can choose the visual theme that best suits my preferences and environment. | Could Have | To Do | - Implement lite and dark mode themes. <br> - Allow users to toggle between themes. | - Develop theme switching functionality. | - Visual appeal of both themes. <br> - Seamless theme switching. | 2 | TBD